## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | No | Auto Scheduled |  | 0 mins |  |  |  | 1
2 | Yes | Auto Scheduled | Source vs Target data validation | 3 days | Fri 12-22-00 | Sun 12-24-00 |  | 1
3 | Yes | Auto Scheduled | Extract data from OhZone | 2 days | Fri 12-22-00 | Sat 12-23-00 |  | 2
4 | Yes | Auto Scheduled | Extract data from sharepoint | 2 days | Fri 12-22-00 | Sat 12-23-00 |  | 2
5 | Yes | Auto Scheduled | Reconcile source vs target | 1 day | Sun 12-24-00 | Sun 12-24-00 | 3;4 | 2
6 | Yes | Manually Scheduled | Workflow Process Finalization | 1 day | Sat 12-23-00 | Sat 12-23-00 |  | 1
7 | Yes | Auto Scheduled | Incidents | 1 day | Sat 12-23-00 | Sat 12-23-00 |  | 2
8 | Yes | Auto Scheduled | Requests | 1 day | Sat 12-23-00 | Sat 12-23-00 |  | 2
9 | Yes | Auto Scheduled | Enhancements | 1 day | Sat 12-23-00 | Sat 12-23-00 |  | 2
10 | Yes | Auto Scheduled | L1 Group setup | 1 day | Fri 12-22-00 | Fri 12-22-00 |  | 1
11 | Yes | Auto Scheduled | Assign right resoruces to L1 Group | 1 day | Fri 12-22-00 | Fri 12-22-00 |  | 2
12 | Yes | Auto Scheduled | communication for Transition to OhZone | 3 days | Fri 12-22-00 | Sun 12-24-00 |  | 1
13 | Yes | Auto Scheduled | Draft notification preparation | 1 day | Fri 12-22-00 | Fri 12-22-00 |  | 2
14 | Yes | Auto Scheduled | send notificaiton | 1 day | Sun 12-24-00 | Sun 12-24-00 | 13;5SS | 2
15 | Yes | Auto Scheduled | OhZone Active | 1 day | Sun 12-24-00 | Sun 12-24-00 | 14SS | 1
16 | Yes | Auto Scheduled |  | 1 day | Fri 12-22-00 | Fri 12-22-00 |  | 1

## Resource_Table
ID | Resource name | Type | Material label | Initials | Group | Max.Units | Std.Rate | Ovt.Rate | Cost/Use | Accrue At | Base Calendar | Code
1 | Soni | Work |  | S |  | 100% | ₹0.00/hr | ₹0.00/hr | ₹ 0.00 | Prorated | Standard
2 | Grace | Work |  | G |  | 100% | ₹0.00/hr | ₹0.00/hr | ₹ 0.00 | Prorated | Standard
3 | Abhiram | Work |  | A |  | 100% | ₹0.00/hr | ₹0.00/hr | ₹ 0.00 | Prorated | Standard
4 | Sanjeev | Work |  | S |  | 100% | ₹0.00/hr | ₹0.00/hr | ₹ 0.00 | Prorated | Standard
5 | TC | Work |  | T |  | 100% | ₹0.00/hr | ₹0.00/hr | ₹ 0.00 | Prorated | Standard
6 | Mark | Work |  | M |  | 100% | ₹0.00/hr | ₹0.00/hr | ₹ 0.00 | Prorated | Standard
7 | Vikas | Work |  | V |  | 100% | ₹0.00/hr | ₹0.00/hr | ₹ 0.00 | Prorated | Standard

## Assignment_Table
ID | Task name | Resource name | Work | Duration
2 | Draft notification preparation | Grace | 8 hrs | 1 day
3 | send notificaiton | Grace | 8 hrs | 1 day
13 | Assign right resoruces to L1 Group | Soni | 8 hrs | 1 day
15 | Reconcile source vs target | Abhiram | 8 hrs | 1 day
16 | Extract data from OhZone | Soni | 16 hrs | 2 days
17 | Extract data from sharepoint | Sanjeev | 16 hrs | 2 days
18 | Incidents | Mark | 8 hrs | 1 day
19 | Requests | Mark | 8 hrs | 1 day
20 | Enhancements | Mark | 8 hrs | 1 day
21 | Incidents | Vikas | 8 hrs | 1 day
22 | Requests | Vikas | 8 hrs | 1 day
23 | Enhancements | Vikas | 8 hrs | 1 day